## Sheet1
Decision Area | Decision Summary | Rationale | Implications / Trade-offs | Next Steps (If Given More Time)
Scope Interpretation & Timeboxing | Focused on implementing API automation using RestAssured and TestNG for 3 key endpoints (/auth, /booking, /booking/{id}) to meet assessment scope. Timeboxed to complete core positive, negative, and boundary cases within allotted period. | Ensured compliance with assessment criteria while balancing thoroughness and deliverability under time constraints. | Limited exploration of edge cases (e.g., concurrent API calls, load testing) due to timeboxing. | Expand test coverage to include performance and concurrency validation; integrate with CI/CD pipeline.
Test Selection & Coverage Rationale | Selected high-value tests targeting authentication, booking creation, and retrieval endpoints. Covered positive, negative, and boundary scenarios per endpoint. | These endpoints represent the most critical business functions and enable end-to-end validation of API flow. | UI tests were deprioritized for stability and focus on backend verification. | Add regression-level scenarios for booking updates (PUT/PATCH) and deletions.
Stability & Data Strategy | Used static sample data and parameterized external JSON datasets to ensure reproducibility. Captured dynamic tokens and booking IDs at runtime for chaining tests. | Promotes repeatable, deterministic test execution and ensures isolation across runs. | No live DB or environment control—relied on API behavior consistency. | Implement data seeding and teardown scripts to achieve true environment reset between runs.
Project Structure Decisions | Adopted modular TestNG + Maven project with separated config, utils, services, and tests layers. Structured resources for schemas and testdata. | Mirrors enterprise automation standards; supports scalability, CI integration, and reusability. | Slightly higher initial setup overhead; minimal if templates are reused. | Add a BaseTest layer to centralize setup/teardown and configuration injection.
Next Steps (Strategic Improvements) | Integrate with Repo for CI execution and reporting. Expand UI automation and link API–UI validations. Add schema versioning for contract tests. | Moves project toward production-grade automation with real CI visibility and quality gates. | Requires more time for environment setup and credential management. | Implement CI pipeline with environment-based configuration management and Allure reporting.